## AR10+Wave300
ID | Category | Test | Description | Pass Criteria | Responsibility | Estimation | Equipment | advisors | remarks | Dependencies
1 | Build |  |  |  |  | 2
1.1 |  | AR10+Wave300 model build | Build AR10+Wave300 model and verify contents of rootfs on build server | Model builds (fullimage available). Wave driver compiles. rootfs folder contains MAPI scripts, hotplug scripts, wireless bins, wireless driver, wireless apps (hostapd/wpa_supplicant), BclSockserver, rc.conf.gz with objects for 1 or 2 wireless devices | Arad | 2 | UGW-5.x from Mercurial and build server |  | rootfs is in: build_dir/target-mips_r2_uClibc-0.9.30.1_2_6_32_ar10_XXX/root-ltqcpe/ | AR10 model that contains PCIe, MAPI and rc.conf.gz and Wave300 support (BLR)
2 | Bringup |  |  |  |  | 5
2.1 |  | Bring up Wave300 on AR10 | Boot image built in 1.1 | rc.bringup_wlan is called by boot sequence wlan0 is up, in ifconfig and in br0 hostapd is up in ps | Arad | 2 | AR10 evaluation board |  |  | AR10 board and BSP available, PCIe functional
2.2 |  | Verify default wireless configuration set by MAPI/rc.conf | Compare parameters in driver with rc.conf/wave300.conf settings | Parameters were written correctly to the driver. Iwprivs return expected results | Arad | 1
2.3 |  | Basic wireless functionality | Scan and connect to AR10 | STA sees AR10 in air STA can connect to AR10 ping passes from AP to STA | Arad | 1
2.4 |  | Verify security configuration | Configure AR10 to WPA2 security, scan STA and connect. Repeat for other security modes. | hostapd configuration file generated correctly for WPA2. STA sees AR10 in air, in WPA2. STA can connect to AR10. ping passes from AP to STA | Arad | 1 |  |  |  | set security scripts which change security mode without web
3 | Wireless tools |  |  |  |  | 3
3.1 |  | BB Studio | Manually start BclSockserver on AR10 and connect BB Studio to AR10 | BclSockServer executes without error, BB Studio can connect, Some forms can be read correctly. | Arad | 1 | PC with BB Studio
3.2 |  | DUT | Compile DUT driver and dutserver for AR10. Add to DUT installation on Windows. Connect DUT GUI to AR10 | DUT can connect, EEPROM can be read/written | Arad | 2 | PC with DUT GUI installation

## AR10+Wave400
ID | Category | Test | Description | Pass Criteria | Responsibility | Estimation | Equipment | advisors | remarks | Dependencies
1 | Build |  |  |  |  | 2
1.1 |  | Build AR10+Wave300 model | Build AR10+Wave300 model and verify contents of rootfs on build server | Model builds (fullimage available). Wave driver compiles. rootfs folder contains MAPI scripts, hotplug scripts, wireless bins, wireless driver, wireless apps (hostapd/wpa_supplicant), BclSockserver, rc.conf.gz with objects for 1 or 2 wireless devices | Assaf | 2 | UGW-5.x from Mercurial and build server |  | rootfs is in: build_dir/target-mips_r2_uClibc-0.9.30.1_2_6_32_ar10_XXX/root-ltqcpe/ | AR10 model that contains PCIe, MAPI and rc.conf.gz and Wave300 support (BLR)
2 | Bringup |  |  |  |  | 5
2.1 |  | Bring up Wave300 on AR10 | Boot image built in 1.1 | rc.bringup_wlan is called by boot sequence wlan0 is up, in ifconfig and in br0 hostapd is up in ps | Assaf | 2 | AR10 evaluation board |  |  | AR10 board and BSP available, PCIe functional
2.2 |  | Verify default wireless configuration set by MAPI/rc.conf | Compare parameters in driver with rc.conf/wave300.conf settings | Parameters were written correctly to the driver. Iwprivs return expected results | Assaf | 1
2.3 |  | Basic wireless functionality | Scan and connect to AR10 | STA sees AR10 in air STA can connect to AR10 ping passes from AP to STA | Assaf | 1
2.4 |  | Verify security configuration | Configure AR10 to WPA2 security, scan STA and connect. Repeat for other security modes. | hostapd configuration file generated correctly for WPA2. STA sees AR10 in air, in WPA2. STA can connect to AR10. ping passes from AP to STA | Assaf | 1 |  |  |  | set security scripts which change security mode without web
2.5 |  | 1 MB DDR reservation (Wave400 only) | Top 1MB of linux reserved for Wave400. Verify with /proc/meminfo | proc/meminfo shows 1MB less than physical available for linux | Assaf | 0
3 | Wireless tools |  |  |  |  | 3
3.1 |  | BB Studio | Manually start BclSockserver on AR10 and connect BB Studio to AR10 | BclSockServer executes without error, BB Studio can connect, Some forms can be read correctly. | Assaf | 1 | PC with BB Studio
3.2 |  | DUT | Compile DUT driver and dutserver for AR10. Add to DUT installation on Windows. Connect DUT GUI to AR10 | DUT can connect, EEPROM can be read/written | Assaf | 2 | PC with DUT GUI installation